# Schedule

March 2018

* Recording samples
* Analyze frequency spectrum of samples
* Research on algorithms

April / May (/ June?) 2018

* Implementation of chosen algorithms in Matlab

June 2018

* Chapter 3 – Pitch detection algorithms

July 2018

* Chapter 6 – Implementation Matlab
* Maybe already some tests for chapter 7

August – September 2018

* Chapter 4 & 5 – Requirements and Concept for the App

October 2018 – January 2019

* Implementation of the App
* Chapter 6 – Implementation App

February 2019

* Chapter 7 – Tests

March 2019

* Chapter 8 – Results

April 2019

* Chapter 1 – Introduction
* Chapter 2 – Related Work

May 2019

* Chapter 9 - Summary